## Sheet1
SNO | Task | Description | Status | Owner | Start Date | End Date | Blockers and Dependencies | Remarks
1 | Understand the current version of the SAQE code | Coordinate with Mohan to obtain and review the current version of the SAQE code for better understanding | In progress | Shridhar Patil | 2025-08-26 | 2025-09-05 | Need access to Windows Server Vizag 192.168.110.110, Need sophos vpn access for vizag | Mohan asked to connect with Praveen,as the code is residing at Windows Server in Vizag 192.168.110.110 , which I need to download and setup in my local
2 | RIM JIRA Setup Walkthrough | Coordinate with Farheen to review the RiM JIRA setup and gain understanding of the data configuration and API details | In progress | Shridhar Patil | 2025-08-26 | 2025-09-05 | SAQE project need to setup in local | Discussion started , received excel sheet for dataset from farheen, showed jira of RIM , later I would need jira credentials
3 | Enhance SAQE code for JIRA data extraction and feature implementation | Predictive test management | Not Started | Shridhar Patil | 2025-09-01 | 2025-09-12 | SAQE project need to setup in local | Allocated 2 working weeks for each task
4 | Enhance SAQE code for JIRA data extraction and feature implementation | Test optimization and prioritization | Not Started | Shridhar Patil | 2025-09-15 | 2025-09-26 | SAQE project need to setup in local | Allocated 2 working weeks for each task
5 | Enhance SAQE code for JIRA data extraction and feature implementation | Defect Predication | Not Started | Shridhar Patil | 2025-09-29 | 2025-10-10 | SAQE project need to setup in local | Allocated 2 working weeks for each task
6 | Enhance SAQE code for JIRA data extraction and feature implementation | Root cause analysis | Not Started | Shridhar Patil | 2025-10-13 | 2025-10-24 | SAQE project need to setup in local | Allocated 2 working weeks for each task
7 | Code Base Analysis | Code Base Analysis | Not Started | Shridhar Patil | 2025-10-27 | 2025-11-07 | SAQE project need to setup in local | Allocated 2 working weeks for each task